## Slide 1
SCRUM Overview
IT Academy Experts’ group
January, 2011
Approved by Ivan Hitskaylo
07.2014

## Slide 2: Scrum Agenda
SCRUM intro
Scrum Release Cycle
Diagram of Flow
Scrum framework
  Roles
  Time boxes
  Artifacts
Summary

## Slide 3: SCRUM Intro
Scrum is the framework which consists of a set of Scrum Teams and their associated roles; Time-Boxes, Artifacts, and Rules.
Scrum Teams:
  Self-organizing and cross-functional;
  work in iterations.
Consists of the following three roles:
  Scrum Master, who is responsible for ensuring the process is understood and followed;
  Product Owner, who is responsible for creation and managing requirements;
  Team, which does the work.

## Slide 4: SCRUM Intro

## Slide 5
Release Cycle
Analysis
Design
Development
Testing
Sprint 1
Sprint 2
Sprint 3
Sprint 4
Sprint 5
Sprint …

## Slide 6: Diagram of Flow

## Slide 7: Diagram of Flow
Scrum projects make progress in a series of “sprints”
  Analogous to Extreme Programming iterations
Typical duration is 2–4 weeks or a calendar month at most
A constant duration leads to a better rhythm
Product is designed, coded, tested and documented during the sprint

## Slide 8: Diagram of Flow
Requirements
Design
Code
Test
Rather than doing all of one thing at a time…
...Scrum teams do a little of everything all the time

## Slide 9: Scrum Framework
Product Owner
Scrum Master
Team
Roles
Sprint
Sprint planning
Daily Scrum
Sprint Review
Sprint Retrospective
Time boxes
Product Backlog
Sprint Backlog
Burndown Charts
Artifacts

## Slide 10: Scrum Framework
Sprint
Sprint Planning
Daily Scrum
Sprint Review
Sprint Retrospective
Time boxes
Product Backlog
Sprint Backlog
Burndown Charts
Artifacts
Product Owner
Scrum Master
Team
Roles

## Slide 11: Scrum Master Role

## Slide 12: Scrum Master
Responsibilities:
Responsible for enacting Scrum values and practices
Removes the barriers between the team and the customer
Ensures that the team is fully functional and productive
Enables close cooperation across all roles and functions
Shields the team from external interferences

## Slide 13: Scrum Master
Responsibilities:
Scrum Master is responsible for the Scrum process
Teaching the organization how to use Scrum
Teaching Product Owner and Team how to fulfill their roles within Scrum process
Facilitating the creativity inside the team
Improving tools and practices used
No authority

## Slide 14: Scrum Master
Who is Scrum Master
“Leader of the band”
“Conductor of the orchestra”
“Sheep dog”

## Slide 15: Product Owner

## Slide 16: Product Owner
Exercise:
You are working at “Fat Burger” and are the only person on duty
A customer approaches and orders a “Double Fat Burger Deluxe” with onions, cheese and bacon with fries and a coke
You ring up the order. The price is $5.65.
The customer informs you that he only has $1.20
What do you do and what do you tell the customer?

## Slide 17: Product Owner
Responsibilities:
Defines the features of the product
Decides on release date and content
Responsible for the profitability of the product (ROI)
Prioritizes features according to market value
Adjusts features and priority every iteration, as needed
Accepts or reject work results

## Slide 18: Prioritization

## Slide 19: Team

## Slide 20: Team
Typically 7+/-2 people
Cross-functional
    Programmers, testers, user experience designers, etc.
Members should be full-time
  May be exceptions (e.g., database administrator)
Teams are self-organizing
  Ideally, no titles but rarely a possibility
Membership should change only between sprints

## Slide 21: Team
Everyone necessary to go from product backlog to potentially shippable product increment, including:
  Programmers
  Testers
  Analysts
  DBAs
  Tech Writers
  UI Designers
  Etc

## Slide 22: Exercise
You are the Scrum Master and …
The analyst on the project wants to work one sprint ahead so that the analysis is ready when the programmers need it
The tech writers want to work one sprint behind so that they are “more efficient.”
What do you do?

## Slide 23: Scrum framework
Product Backlog
Sprint Backlog
Burndown Charts
Artifacts
Product Owner
Scrum Master
Team
Roles
Sprint
Sprint Planning
Daily Scrum
Sprint Review
Sprint Retrospective
Time boxes

## Slide 24: Sprint

## Slide 25: Sprint
2-4 weeks sprint
Sprint planning
4/4 hrs
Sprint Review and Retrospectives
4/4 hrs
Development Work

## Slide 26: Sprint
2-4 weeks iteration
Team does work from product backlog
Team commits to achieve the sprint goal
Team plans work for sprint on a Sprint Planning meeting
Team demos work completed on a Sprint Review Meeting
Every day team highlights progress on a Daily Scrum meeting
Sprint Burndown chart is used to visualize team progress

## Slide 27: Sprint
Abnormal Termination
Sprint can be cancelled if Team cannot meet Sprint goals
Management can cancel Sprint if external circumstances breaks Sprint goal
If Sprint is terminated, next step is to have next Sprint Planning meeting, review the reason of termination and start another Sprint

## Slide 28: Sprint Planning

## Slide 29: Sprint Planning
Sprint Planning Meeting
Sprint Prioritization
Analyze and evaluate Product Backlog
Select sprint goal
Sprint Prioritization
Decide how to achieve sprint goal (design)
Create sprint backlog (tasks) from product backlog items (user stories / features)
Estimate sprint backlog in hours
Team
Capacity
Product
Backlog
Technology
Sprint
Goal
Sprint
Backlog

## Slide 30: Sprint Planning
Team selects items from the product backlog they can commit to completing
Sprint backlog is created
    Tasks are identified and each is estimated (1-16 hours)
    Collaboratively, not done alone by the Scrum Master
High-level design is considered

## Slide 31: Sprint Planning
As a vacation planner, I want to see photos of the hotels.
Code the middle tier (8 hours)
Code the user interface (4 hours)
Write test fixtures (4 hours)
Code the foo class (6 hours)
Update performance tests (4 hours)

## Slide 32: Daily Scrum

## Slide 33: Daily Scrum
Parameters
  Daily
  15-minutes
  Stand-up
Not for problem solving
  Whole world is invited
  Only team members, Scrum Master, Product Owner can talk
Helps avoid other unnecessary meetings

## Slide 34: Daily Scrum
Progress Documents
Sprint Tracker/Sprint Backlog
Sprint Burndown Chart
Whiteboard
Scrum Tools
  Excel
  Version One
  Rally
  Etc.

## Slide 35: Daily Scrum

## Slide 36: Daily Scrum
Everyone answers 3 questions, which aren’t not status for the Scrum Master, but they are commitments in front of peers
What did you do yesterday?
What will you do today?
Is anything on your way?
1
2
3

## Slide 37: Sprint Review

## Slide 38: Sprint Review
Team presents what it accomplished during the sprint
Typically takes the form of a demo of new features or underlying architecture
Informal
    2-hour prep time rule
    No slides
Whole team participates
Invite the world

## Slide 39: Sprint Review
Unfinished work goes to the Product Backlog.
Update the Product Backlog based on work completed by the team – expected and unexpected.
Reformulate the team – do we have the “right” team members for the next sprint.
Reprioritizing the Product Backlog to take advantage of opportunities that the completed work presents.
Requesting that the project progress be sped up by authorizing additional teams to work on the Product Backlog.

## Slide 40: Sprint Retrospective
Periodically take a look at what is and is not working
Typically 15–30 minutes
Done after every sprint
Whole team participates
    Scrum Master
    Product owner
    Team
    Possibly customers and others

## Slide 41: Sprint Retrospective
Whole team gathers and discusses what they’d like to:
Start doing
Continue doing
Stop doing

## Slide 42: Sprint Retrospective
Team selects 3-5 most important items to address
At the beginning of each retrospective meeting team reviews items that were selected previous time

## Slide 43: Scrum Framework
Product Owner
Scrum Master
Team
Roles
Sprint
Sprint Planning
Daily Scrum
Sprint Review
Sprint Retrospective
Time boxes
Product Backlog
Sprint Backlog
Burndown Charts
Artifacts

## Slide 44: Product Backlog

## Slide 45: Product Backlog
Where IT Meets The Business
IT
Business

## Slide 46: Product Backlog
The requirements
A list of all desired work on the project
Ideally expressed such that each item has value to the users or customers of the product
Prioritized by the product owner
Reprioritized at the start of each sprint
This is the product backlog

## Slide 47: Product Backlog
Requirement | Priority
Set up Christmas Tree in living room | 10
Decorate windows in New Year style | 20
Organize sitting place | 30
Organize listening the music | 40
Cook different dishes to the holiday table | 50
... | 60

## Slide 48: User Story
User stories are short, clear description of the functionality that will be valuable for the customer or user of the product
Benefits of User Stories:
  Stories shift focus from writing to talking
  Stories are understandable by users and developers
  Stories support iterative development
  Stories are the right size for planning

## Slide 49: User Story
As a <type of user>, I can <goal> so that <reason>
User Story Template

## Slide 50: User Story
As a guest, I want to have ability to listen the music
As a house owner, I want to see Christmas Tree in living room
As a guest, I want to have sitting place

## Slide 51: User Story
Backlog item | Estimate (story points)
As a house owner, I want to see Christmas Tree in living room | 8
As a house owner, I want to have New Year decorated windows | 5
As a guest, I want to have sitting place | 1
As a guest, I want to have ability to listen the music | 3
As a guest, I want to have different dishes on the holiday table | 21
... | 30
Product Backlog with User Stories

## Slide 52: User Stories Characteristics
Independent
Negotiable
Valuable
Estimatable
Small
Testable

## Slide 53: User Stories
[Olha] I propose to delete this example at all
Exercise:
Write the following user stories
  System should work on Windows XP
  Rewrite SQL select statement to decrease time of its execution
  Build system should build the sources and run unit tests every night

## Slide 54: User Stories
What is DONE?
When is user story done for:
  Programmer
  Tester
  User Experience Designer
  DB Architect
  ?
When is user story done for customer?

## Slide 55: User Story
A story is complete (DONE) when:
Coded/implemented
Peer reviewed (pair programming counts as peer review)
Code is run against current version in source control
Code is commented in source control and checked in
Acceptance test suites are updated and executed with no failures
All critical and blocker bugs found in acceptance test are resolved and verified
Unit Tests written and passing (0 failing in your build components)

## Slide 56: User Story
Performance Unit Tests written and passing and no regression on existing Performance Unit Tests
Code coverage of unit tests must not regress
Test Strategies are updated and reviewed by the team
All development-based doc items (including Java Docs) are completed
Performance Review by performance architect* (*for items requiring review)
UI Reviewed with UE representative on team* (*for UI-oriented items)

## Slide 57: Estimation and Planning
Exercise:
What is the distance to:
  Kyiv
  London
  Tokyo
How long it will take to travel to these cities?
Which one is the longest/shortest distance?

## Slide 58: Estimation and Planning
The “bigness” of task
Unit-less values
Relative values
Typically Fibonacci numbers are used except 2:
  1, 3, 5, 8, 13
Other options
  T-Shirt sizes: XS, S, M, L, XL, …

## Slide 59: Estimation and Planning
Dogs
Bulldog (бульдог)
Pekingese (пекінес)
Doberman (доберман)
Poodle (пудель)
Dog (дог)
Evaluated size
M
XS
L
S
XL

## Slide 60: Estimation and Planning
Story Points Advantages
Drive cross-functional behavior
  Allows apple to apple comparison
Pure measure of size
Estimation is fast
Estimating the size not the duration
  Duration is determined empirically by seeing how much is complete per sprint
Units can be added together
  Time estimates are not additive

## Slide 61: Planning Poker
An iterative approach to estimating
Steps
  Each estimator is given a deck of cards, each card has a valid estimate written on it
  Product owner reads a story and it’s discussed briefly
  Each estimator selects a card that’s his or her estimate
  Cards are turned over so all can see them
  Discuss differences (especially outliers)
  Re-estimate until estimates converge

## Slide 62: Planning Poker
Estimate these
Product backlog item | Estimate
Read a high-level, 10 page overview of agile software development in magazine | 
Write the product backlog for your friend who owns the clock store and now wants an ecommerce site | 
Recruit, interview and hire new member to your team | 
Read a 150-page of art book | 
Wash your boss’ car | 

## Slide 63: Sprint Backlog
The sprint goal is a short statement of what the work will be focused on during the sprint
Examples of goals:
  Make the application run on SQL Server in addition to Oracle.
  Support more technical indicators than company ABC with real-time, streaming data.
  Support features necessary for population genetics studies.

## Slide 64: Sprint Backlog
Managing Sprint Backlog
Individuals sign up for work of their own choosing (Work is never assigned)
Estimated work remaining is updated daily
Any team member can add, delete or change the sprint backlog
Work for the sprint emerges
If work is unclear, define a sprint backlog item with a larger amount of time and break it down later
Update work remaining as more becomes known

## Slide 65: Product Backlog
Backlog item | Estimate (story points)
As a house owner, I want to see Christmas Tree in living room | 8
As a house owner, I want to have New Year decorated windows | 5
As a guest, I want to have sitting place | 1
As a guest, I want to have ability to listen the music | 3
As a guest, I want to have different dishes on the holiday table | 21
... | 30

## Slide 66: Sprint Backlog
Tasks | Mon | Tue | Wed | Thur | Fri
As a mother, I want to see Christmas tree in living room |  |  |  |  | 
Select and measure a place for the Christmas Tree | 1 | 0 | 0 | 0 | 0
Select color, size and style for Christmas decorations (toys, Christmas tree ornaments etc) | 3 | 0 | 0 | 0 | 0
Buy Christmas Tree | 4 | 0 | 0 | 0 | 0
Buy Christmas decorations | 8 | 8 | 6 | 7 | 0
Install Christmas Tree | 0.5 | 0.5 | 0.5 | 0 | 0
Decorate the Christmas Tree | 3 | 3 | 3 | 3 | 3
As mother to take a look if this is what she expected | 0.5 | 0.5 | 0.5 | 0.5 | 0.5

## Slide 67: Sprint Burn Down Chart
Chart: 
| 17/1/2011 | 18/1/2011 | 19/1/2011 | 20/1/2011 | 21/1/2011
 | 20 | 12 | 10 | 10.5 | 3.5
 | 20 | 15 | 10 | 5 | 0

## Slide 69: Questions
Thank You!
Copyright © 2010 SoftServe, Inc.